## Sheet1
Mount Hood Chapter, PCTA
Project Paperwork Summary - One Day Projects
| Form Name | Purpose | Procedure | During project | After project
| Crew Leader Checklist | Provides list of actions needed to complete a project. | Use as reference for plannng and timing of project requirements |  | Recycle
| Volunteer Sign-up sheet | Ensures volunteers receive information on liability coverage and release PCTA of liability. Required by PCTA and USFS. | Each volunteer signs at the trailhead. Collect round-trip travel time and Emergency Contact from volunteers. | Crew Leader carries the form during project. | Send to PCTA (#)
| Tool Checkout Form | Provides a checklist for tracking tools. | Use to record tools taken for project and tools returned. |  | Recycle
SAFETY | Job Hazard Analysis (JHA) | Ensures volunteers receive information on tasks to be performed, possible hazards related to tasks, and abatement actions. Required by USFS. Will include one or more for specific project types such as: -Trail Maintenance -Crosscut Saw Use -Chainsaw Use | Each volunteer signs at the trailhead. Review during the Tailgate Safety Session. |  | Send signature page(s) to PCTA (#)
| Trailhead Communications Plan (TCP) | Provides important logistics information in the event of an emergency. Required by JHA. | Prepared beforehand and emailed to Dispatch and Agency partners. Cc to Regional Rep and Chapter Chair. | Three copies carried: 1-First Aid lead 2-Communications lead 3-Crew Leader | Update and re-use for future projects at same location.
|  | Lists leadership roles in the event of an emergency. | Assign at TH: - Situation Manager - First Aid Lead - Communications Lead
| Emergency Action Plan (EAP) | Provides important steps to follow before and in the event of an emergency. Required by JHA. | Use as reference when dealing with an emergency. | Carried with TCP and in First Aid kit | Recycle
| Tailgate Safety Session checklist (TSS) | Provides a checklist of important topics to cover during safety session. | Use at trail head as reference for topics to discuss |  | Recycle
| Project Report Summary | Provides PCTA with volunteer hours and project accomplishments. | Complete online form on PCTA website after the project. |  | Submit online at pcta.org, cc Regional Rep, Agency Partner, Chapter Chair.
| (#) | PCTA, attn: Volunteer Programs, 1331 Garden Hwy, Sacramento, Ca 95833
|  | (can be sent by USPS or scanned and emailed) |  |  | Oct 2014