## Sheet1
|  | Mount Hood Chapter, PCTA |  | revised 6/18/18
Crew Leader Checklist - One Day Projects
Project Name: __________________________ Project Date: ____________Crew Leader:___________________
When | Ck-Off |  | Task | minimum required | X
Prior weeks |  | Scout section, document maintenance needs
Develop Project Plan: ie; Logout, Brushing, Drainage/Slides, Tread work
determine project location, date, work to do, crew size.
use Tool Checkout Form to plan tools needed for project
create Recruitment memo with input for Eventbrite listing
|  | update Trailhead Communications Plan (TCP) add current date, project description |  |  | X
2 days before the 1st & 15th |  | email Recruitment Memo for Eventbrite to Volunteer Coordinator (cc Mt Hood Chair)
Eventbrite postings will be on the 1st and 15th of each month, send in two day earlier
list crew size, project name, date/time, trailhead, project overview/trail/work descr.
also include hike distance, special notes, driving directions, JHA(s) to use
week before |  | e-mail Agency Contact about work trip (cc Regional Rep & Mt Hood Chair) |  |  | X
receive volunteer crew names and emails from Volunteer Coordinator
Crew will receive details thru Eventbrite
receive Volunteer Sign-up form pre-filled in with crew names and details from PCTA
Pick-up Tools and safety gear from Tool Cache (use Tool Checkout form)
Ensure all tools and gear are clean and functioning.
keep copy of Tool Checkout Form to track tools during the project
Assemble Forms for use at trail head (put in case to carry to TH)
print Volunteer Sign-up sheets
|  |  | print Job Hazard Analysis(s) (JHA) | review prior to project
print updated Trailhead Communications Plan (TCP) - 3 copies
|  |  | print Emergency Action Plan (EAP) (print on back of TCP) | review prior to project
|  |  | print Tailgate Safety Session checklist (TSS) | review prior to project
include copy of Tool Checkout Form
include clipboards and pens for signing forms at trail head (Sign-up, JHA's)
day before |  | e-mail TCP to Dispatch & Agency Contact, (cc Regional Rep, Mt Hood Chair) |  |  | X
send on Friday for work crew on Sat, Sun, Mon
get final crew list from Volunteer Coordinator, in case of last minute changes/additions
day of project |  | Arrive early at Trailhead - Layout tools and gear for crew to use.
Greet Crew at trailhead, volunteer introductions and questions.
|  |  | ensure all sign JHA and Sign-up (include emergency contact, travel time) |  | X
Discuss Project Goals, review tool types and uses
|  | Discuss Trail Safety (see Tailgate Safety Session checklist) |  |  | X
Review JHA, PPE, TCP, EAP, Tool safety
Distribute group FA kit and radios
|  | Call Dispatch before starting work (use cell phone or radio) |  |  | X
during day |  | Work Safely, Have Fun, Get some Work done
Encourage proper tool use, Don't overwork, Take breaks
Record time on trail and work done, for later input to Project Report
Take photos of project area, before and after work, to document accomplishments
end of day |  | Call Dispatch after returning to TH |  |  | X
Collect Tools, clean if neccessary (use copy of Tool Checkout form as reference)
day after |  | e-mail Thank You note to volunteers with a few photos
|  | Submit online Project Report Summary to PCTA (pcta.org/volunteer/crew-leader-center) |  |  | X
Send forms to PCTA: Sign-up sheets and JHA signature pages.(usps or scan/email)
Return Tools to Cache (clean and repair if needed).