## Sheet1
Crew Leader Checklist for Burn Area Crews
Mount Hood Chapter PCTA | revised 10/10/2019
WEEK BEFORE
Ensure volunteers will have sufficient on-site supervision to work safely; two crew leaders for each crew.
Update Trailhead Communications Plan (TCP); add current date and project description.
Pick up tools and PPE for crew from cache.
DAY BEFORE
Check weather forecast and have backup plans in case of forecast of winds or heavy rains.
Email TCP to Columbia Dispatch (waccc@firenet.gov)
& Agency Contacts (Nathaniel Brodie, nathaniel.brodie@usda.gov and Edan Lira, elira@fs.fed.us)
If working on closed trail send also to jesus.armenta@usda.gov and carissa.silvis@usda.gov
(cc Regional Rep (dhendricks@pcta.org) & Mt Hood Chair (lhovin@pcta.org)
Get final crew list from Volunteer Coordinator, in case of last minute changes/additions.
DAY OF PROJECT
Review and sign Trail Maintenance Job Hazard Analysis (JHA) with crew.
for "pg 4-Specific Concerns", check the Burned Area Job Hazard Analysis (JHA).
Review Trail Communications Plan (TCP) and Emergency Action Plan (EAP).
Review Tailgate Safety Session checklist (TSS).
Ensure all fill out Sign-up sheet, including emergency contact.
Check in with Columbia Dispatch (cell phone or radio) or Alternate Dispatch (see below)
an Alternate Dispatch is allowed for trails other than Eagle Creek (which has insufficient cell coverage).
Minimize the number of cars at publicly visible but closed trailheads.
DURING
Monitor weather throughout the day and adjust the work plan as needed.
Discontinue assessment and repair work if encountering increasing winds or heavy rains.
Consider midday check in with Columbia Dispatch.
Be alert for hazardous trees along the trail.
Flag any trees, logs, or other hazards you encounter and GPS locations if possible.
Be alert for potential rolling material above the trail.
Walk through high risk areas one at a time with others serving as lookouts.
Work in pairs or more.
First and Last person on trail must have radios
AFTER
Check out with Columbia Dispatch.
Please report any near misses or safety concerns
Submit online PCTA Project Report Summary
Return tools and send Thank You note to crew and cc Agency Contacts.